## Project Information
Job Name: | Avonworth E.S.
Job Number: | EP2242685
Salesperson: | Sean Davis
Primary Contact Name: | Brandon Gary
Primary Contact Phone: | Cell: 724-601-6272 // 412-369-8738 x1507
Primary Contact Email: | bgary@avonworth.k12.pa.us
Alternate #1 Contact Name:
Alternate #1 Contact Phone:
Alternate #1 Contact Email:
Alternate #2 Contact Name:
Alternate #2 Contact Phone:
Alternate #2 Contact Email:
Install Address: | 1320 Roosevelt Rd. Pittsburgh, PA 15237
Customer's P. O. #: | 22000033
SCOPE OF WORK
Install: (7) SBID-MX286-V, (7) DMU-TV, (7) HDMI 5m Rooms: 184, 185, 201, 202, 207, 208, 209
PROJECT NOTES

## Bill of Materials
Avonworth E.S. | [5 empty] | Job Number: EP2242685
Item Description | Manufacturer Part # | Vendor | Qty | SST PO # | Shipped Via | Tracking # | Received Where | Received By | Received Date

## Technician Testing Checklist
Job Name: Avonworth E.S.
Job Number: EP2242685
Functional Operation Test Checklist | Tested þ | Comments
OFE equipment tested before De-Installation | £
Proper fastening hardware used/Use all holes in brackets for fastening … togglers & bolts or tapcons…etc | £
SMART Board or Display functions to manufacturer's specifications. | £
Sound System-functions with no distortion. All source input tested. | £
Test video – computer – laptop. | £
Projector/Display produces clear image on screen and is aligned | £
All source inputs function. | £
Control System functions properly and controls classroom media equipment. | £
Cable Cubby Cables – Provides connections for walk-in use. | £
Document Camera – functions to manufacturer’s specifications. | £
Cable Management -- neat and tidy. (No cables laying on floor) | £
Room cleared of trash / Equipment cleaned & wiped down. (No Finger Prints) | £
£
£
£
£
£
Pictures Taken | £

## Job Cost Summary
Job Name: | Avonworth E.S. |  |  | Job Number: | EP2242685
Dates: |  |  |  | Sales Rep: | Sean Davis
LABOR
Date(s): à | 2022-09-22
Technician(s): â | [7 empty] | HOURS | RATE | Brate | Burden | LABOR
Dan | 5 | [6 empty] | 5 | 32.7 | 32.3 | 161.5 | 163.5
Chris | 8 | [6 empty] | 8 | 24 | 21 | 168 | 192
Matt | 8 | [6 empty] | 8 | 24 | 21 | 168 | 192
Ihael | 8 | [6 empty] | 8 | 19 | 26 | 208 | 152
Rahman | 8 | [6 empty] | 8 | 18 | 27 | 216 | 144
Travel Time: | [7 empty] | 0 |  |  | 0 | 0
CABLES & CONNECTORS USED: NOT ON BILL OF MATERIALS (INCLUDING ON-SITE PURCHASES) | [7 empty] | Total Labor |  |  | 921.5 | 843.5
Description & Model # |  |  |  | Manufacturer |  | Qty | Cost Each
0
0
0
0
0
0
0
0
0
0
0
HARDWARE USED: NOT ON BILL OF MATERIALS (INCLUDING ON-SITE PURCHASES) | [7 empty] | Total Cables & Connectors |  |  |  | 0
Description & Model # |  |  |  | Manufacturer |  | Qty | Cost Each
Msc. Hardware/Cable Ties/Washers |  |  |  | SST |  | 7 | 3 |  |  |  |  | 21
1/4" Toggler |  | BB100 |  | CTS |  | 56 | 0.35 |  |  |  |  | 19.6
1/4" x 3" Hex Head Bolt |  | CS14X3 |  | CTS |  | 56 | 0.14 |  |  |  |  | 7.84
Expandable Sleeving, 1" |  | GP-803B |  | Nelco |  | 105 | 0.3 |  |  |  |  | 31.5
0
0
0
0
0
EQUIPMENT, CABLES & HARDWARE ON BILL OF MATERIALS BUT NOT USED (RETURNED TO OFFICE) | [7 empty] | Total Hardware |  |  |  | 79.94
Description & Model # |  |  |  | Manufacturer |  | Qty | Cost Each
0
0
0
0
0
0
TRAVEL & LODGING | [7 empty] | Total Returns |  |  |  | 0
Technician(s): à
Air fare: | [11 empty] | 0
Hotel: | [11 empty] | 0
Rental Truck: | 102.49 | [10 empty] | 102.49
Parking/Tolls: | [11 empty] | 0
Per Diem: | [11 empty] | 0
Gas: | [11 empty] | 0
[9 empty] | Total Mileage: |  |  | 22.8
Total Labor |  | 843.5 |  | Miles RT: | 20 |  |  | Total Travel |  |  |  | 125.29
Total Burden |  | 921.5
Total Cables & Connectors |  | 0 |  | Trips: | 2
Total Hardware |  | 79.94 |  | Rate/Mile: | 0.57
Total Returns |  | 0 |  | Total Mileage | 22.8
Total Travel |  | 125.29
Total Install Cost |  | 1970.23
Billed Cost |  | 3850
Actual Cost |  | 1970.23
Profit/Loss & Margin |  | 1879.77 | 48.83%

## Serial Numbers
Job Name: | Avonworth E.S.
Job Number: | EP2242685
Description | Manufacturer | Model | Serial # | Room #/Name | Location

## Equipment Location Approval
Date:
Job Name: | Avonworth E.S.
Job Number: | EP2242685
Building #/Name:
Address: | 1320 Roosevelt Rd. Pittsburgh, PA 15237
Room #/Name:
Equipment to be installed:
Comments:
Equipment to be installed:
Comments:
Equipment to be installed:
Comments:
Equipment to be installed:
Comments:
Equipment to be installed:
Comments:
I have reviewed the above and am satisfied with each of the described locations for installing the equipment and/or wall boxes and indicate such with my initials. I understand I must provide approval before any equipment, racks, mounts, or wall boxes will be installed. If, after approval, I request that the location be changed, I understand there may be additional costs in time and materials, and possibly new hardware, for relocating the unit to a new location.
Owner's or Authorized Representative's Signature |  | Date

## Acceptance Sign-off
Job Name: | Avonworth E.S.
Job Number: | EP2242685
Customer's PO #: | 22000033
SMARTSolution Technologies LP has completed the installation and testing of all systems for this project. By signing this Acceptance Form, the Owner/Authorized Representative agrees that all work has been performed and completed to the Owner's/Authorized Representative satisfaction and that final payment is due within thirty (30) days of the date written below. All equipment remains the property of SMARTSolution Technologies until invoice is paid in full.
SMARTSOLUTION TECHNOLOGIES LP |  | OWNER OR AUTHORIZED REPRESENTATIVE
Technician's Signature |  | Owner's or Authorized Representative's Signature
Printed Name |  | Printed Name and Title
Date |  | Date
813 W North Avenue
Pittsburgh, PA 15210
Phone 412-390-0803 Fax 412-390-0824
www.smarterguys.com